## Sheet1
Overall Objectives | Tasks for Objective | Start Date | Duration | End Date | Team Member
Preliminary | Team Assignment | 2015-08-28 | 1 | 2015-08-29 | Everyone
| Set Up GitHub | 2015-08-28 | 1 | 2015-08-29 | Everyone
Milestone 1 | Main Interface - Menu | 2015-08-28 | 27 | 2015-09-24 | Keegan and Thom
| RSS Feeds Engine | 2015-09-11 | 6 | 2015-08-17 | Drew
| SRS | 2015-09-20 | 4 | 2015-08-24 | Everyone
Milestone 2 | Software Analysis Requirements, Design Phase 1 | 2015-09-30 | 3 | 2015-10-03 | Corey
| Gantt Chart | 2015-10-01 | 2 | 2015-10-03 | Drew
| Fetch Data From an RSS Feed | 2015-09-11 | 6 | 2015-08-17 | Drew
| Refresh UI | 2015-10-03 | 6 | 2015-10-09
| Display Articles | 2015-10-03 | 6 | 2015-10-09
Milestone 3 | Software Design Document, Deisgn Phase 2 | 2015-10-10 | 20 | 2015-10-30
| Keeping Track of Read and Unread Articles | 2015-10-10 | 20 | 2015-10-30
| Saving and Loading user configurations | 2015-10-10 | 20 | 2015-10-30
| Implementing Topics and Keywords | 2015-10-10 | 20 | 2015-10-30
Milestone 4 | Secret Feature | 2015-11-09 | 4 | 2015-11-13
| Topic Interface Completion | 2015-10-30 | 14 | 2015-11-13
| Locating Articles on Map | 2015-10-30 | 14 | 2015-11-13
Milestone 5 | Display Locatable RSS Feeds on the Map and Icon | 2015-11-13 | 21 | 2015-12-04
| Open pop-up message on map interface with link | 2015-11-13 | 21 | 2015-12-04
| Implement Time Filtering | 2015-11-13 | 21 | 2015-12-04
Product Release and Presentation | Complete extra features and basic testing | 2015-12-04 | 7 | 2015-12-04